GrounUp Enterprise Specification
Phase 26 - Estimating, Cost, Production, Crew/Equipment, Haul/Disposal, Markup & Execution Engine

Version 1.0.0 | Implementation-ready specification

# 1. Mission

Implement the deterministic calculation and lifecycle engine that converts scope, quantities and Phase 25 governed library data into reproducible direct cost, production, duration, hauling, markup and sell-price outputs.

# 2. Phase 25 Dependency

Every authoritative estimate uses an immutable Phase 25 snapshot or explicit immutable record versions for service/resource/rate inputs. This prevents historical estimates from changing when live libraries change.

# 3. Production, Crew and Duration

Production drives duration; duration drives crew labor and participating equipment runtime. Crew-size and equipment alternatives can be compared without losing source assumptions.

# 4. Equipment and Fuel

Equipment rate selection uses governed hourly/daily/weekly/monthly policy. Fuel consumption is calculated from runtime and configured consumption/load assumptions.

# 5. Trucking, Haul and Disposal

The engine models load, outbound, dump/queue, return and delay time; trips, truck count and hourly/trip cost are explicit. Disposal uses governed quantity/tonnage conversions and fees.

# 6. Cost Rollup

Labor, equipment, fuel, material, subcontract, trucking, disposal, mobilization and other governed direct costs roll into deterministic direct cost.

# 7. Markup and Sell Price

Indirects, contingency, overhead, profit, tax and bond follow configured calculation bases and order. Parallel and stacked methods are not silently interchanged.

# 8. Scenarios and Confidence

Low/base/high and alternate methods preserve explicit assumption sets. Confidence reflects controlled evidence/completeness/review factors rather than hidden AI judgment.

# 9. AI Estimate Assist

AI may suggest mappings, assumptions, risks, crews and equipment alternatives with evidence/confidence, but authoritative values change only through explicit user/governed actions.

# 10. Writeback and Handoff

Approved new services/assemblies can flow to Phase 25 through governed writeback. Approved/frozen estimate versions export exact baseline/version/snapshot data to proposals and job costing.

# 11. Implementation Modules

P26-MOD-001 - Estimate Service (Domain): Estimate header, lifecycle, versions, ownership, status and approval

P26-MOD-002 - Estimate Line Service (Domain): Service/line-item selection, quantities, units, notes and source evidence

P26-MOD-003 - Assembly Expansion Engine (Engine): Expand versioned assemblies into estimate resource components

P26-MOD-004 - Library Snapshot Resolver (Engine): Resolve immutable Phase 25 library snapshot/version inputs

P26-MOD-005 - Quantity Engine (Engine): Normalize input/takeoff quantities and approved unit conversions

P26-MOD-006 - Production Engine (Engine): Determine base production and modifiers for task/scenario

P26-MOD-007 - Crew Engine (Engine): Resolve crew composition, crew size, labor hours and crew alternatives

P26-MOD-008 - Labor Cost Engine (Engine): Base labor + burden + overtime/shift rules where configured

P26-MOD-009 - Equipment Selection Engine (Engine): Select compatible equipment class/model options for work

P26-MOD-010 - Equipment Cost Engine (Engine): Apply hourly/daily/weekly/monthly rate policy to required duration

P26-MOD-011 - Fuel Engine (Engine): Estimate fuel quantity/cost from configured consumption and runtime assumptions

P26-MOD-012 - Truck Cycle Engine (Engine): Load/haul/dump/return cycle model with capacity and delays

P26-MOD-013 - Truck Count Engine (Engine): Determine truck count required to balance source/placement production

P26-MOD-014 - Haul Cost Engine (Engine): Trip/hour/load-based hauling cost with distance and cycle evidence

P26-MOD-015 - Disposal Engine (Engine): Disposal quantity/fee/tonnage and facility/source logic

P26-MOD-016 - Material Cost Engine (Engine): Material quantity, waste, price, freight/source and unit conversion

P26-MOD-017 - Subcontract Cost Engine (Engine): Subcontract quantity/rate/quote resolution

P26-MOD-018 - Duration Engine (Engine): Work quantity divided by governing production adjusted for shifts/calendars

P26-MOD-019 - Mobilization Engine (Engine): Equipment/crew mobilization and demobilization cost/time

P26-MOD-020 - Indirect Cost Engine (Engine): Project-specific indirect/general-condition allocation

P26-MOD-021 - Regionalization Engine (Engine): Apply allowed regional/location profile factors without double adjustment

P26-MOD-022 - Markup Engine (Engine): Configured markup sequence, overhead, profit, contingency and exclusions

P26-MOD-023 - Tax & Bond Engine (Engine): Configured tax/bond treatment and calculation basis

P26-MOD-024 - Unit Price Engine (Engine): Calculate sell unit price from total sell amount and quantity

P26-MOD-025 - Scenario Engine (Engine): Low/base/high and alternate crew/equipment/haul/shift comparisons

P26-MOD-026 - Confidence Engine (Engine): Input completeness/source age/override/review confidence scoring

P26-MOD-027 - AI Estimate Assist (AI): Suggest mappings/assumptions/risks with evidence; never silently changes approved estimate

P26-MOD-028 - Estimate Review Workflow (Governance): Review, approval, exceptions and estimate freeze

P26-MOD-029 - Service Catalog Writeback (Integration): Approved new service/assembly definitions written to Phase 25 catalog

P26-MOD-030 - Estimate Baseline Export (Integration): Proposal/job-cost/schedule/project handoff with immutable estimate baseline

# 12. Formula Registry

P26-FRM-001 - Duration Hours: quantity / production_rate | Control: quantity and production rate must have compatible output units

P26-FRM-002 - Crew Labor Hours: duration_hours * crew_member_count | Control: sum across crew roles

P26-FRM-003 - Labor Cost: labor_hours * loaded_labor_rate | Control: or explicit base + burden components

P26-FRM-004 - Equipment Cost: selected_rate_policy(runtime, hourly,daily,weekly,monthly) | Control: rate policy governs cheapest/contracted/actual rental basis

P26-FRM-005 - Fuel Quantity: runtime_hours * fuel_consumption_per_hour * load_factor | Control: load_factor optional/default per policy

P26-FRM-006 - Fuel Cost: fuel_quantity * fuel_unit_price | Control: effective-dated fuel price

P26-FRM-007 - Truck Cycle Minutes: load + outbound + dump_queue + return + delays | Control: all components explicit

P26-FRM-008 - Truck Trips: ceil(haul_quantity / effective_payload) | Control: unless partial-load policy differs

P26-FRM-009 - Truck Count: ceil(source_production_per_hour * cycle_hours / payload) | Control: balance rule may use target utilization/buffer

P26-FRM-010 - Hourly Haul Cost: truck_count * truck_hourly_rate * haul_duration_hours | Control: plus configured mobilization/fees

P26-FRM-011 - Trip Haul Cost: trips * trip_rate | Control: trip rate may derive from cycle and hourly rate

P26-FRM-012 - Disposal Tons: volume * approved_density_conversion | Control: only when density is governed

P26-FRM-013 - Material Purchase Qty: installed_qty * (1 + waste_factor) | Control: waste factor decimal

P26-FRM-014 - Material Cost: purchase_qty * unit_price + configured freight | Control: regional/vendor rule applies

P26-FRM-015 - Direct Cost: sum governed direct cost components | Control: component categories explicit

P26-FRM-016 - Sell Price: apply configured markup/contingency/O&P/tax/bond sequence to governed bases | Control: parallel vs stacked preserved

P26-FRM-017 - Unit Sell Price: sell_price / priced_quantity | Control: quantity > 0

P26-FRM-018 - Production Adjusted: base_production * product_of_applicable_rate_modifiers | Control: if modifier policy is production-based

P26-FRM-019 - Duration Adjusted: base_duration * product_of_applicable_duration_modifiers | Control: if modifier policy is duration-based

P26-FRM-020 - Confidence: weighted score of input/source/review factors | Control: weights/version governed

# 13. Controlled Counts

Requirements: 450

Tests: 450

Modules: 30

Entities: 40

Apis: 30

Events: 19

Business Rules: 25

Formulas: 20

Security Controls: 12

Quality Gates: 14